## Lists
Dropdown lists and lookup tables. Formulas on other sheets point at these ranges - do not reorder or insert rows.
Status | Stage 1 category | Q1 What starts it | Q2 Where it lands | Q2b Connectivity | Q3 Reach | Q4 Permissions | Q5 Data class | Q6 Know or do | Q7 Connection | Q8a Wrong answer | Q8b Silent failure | Yes / No | Assurance tier | Verb | Benefit type | Hard or soft | Gate status | Ladder rung | Owning team | Phase | Agent shape
Not started | Automation | A person asks | No interface | Always connected | 1 Me | Acts as the user | Public | Nothing | Yes, in production | Read only | Nothing | Yes | Light touch | Assist | Time or cost released | Hard | Not met | 1 Not AI | Platform team | a Interim | Single agent
In discovery | Predictive or optimisation | A person is already working | Inside the tool they have open | Intermittent | 2 My team | Acts as itself (service identity) | Internal | Static documents | Yes, but not to this system | Writes to a system | Work is delayed | No | Owner approves | Delegate | Error and rework reduction | Soft | In progress | 2 Ready-made | Workload team | b Target | Multi-agent: compliance boundary
Contract agreed | Retrieval | A system event | Collaboration surface | Must work offline | 3 Function |  | Confidential | Analytical data | No | Real-world effect | A person is affected | Unknown | Controlled pilot | Monitor | Speed and responsiveness | Hard or soft | Met | 3 Low-code | AI Centre of Excellence | Single | Multi-agent: multiple teams
Scored | LLM-augmented workflow | A schedule | Embedded in a line of business app | Not applicable | 4 Enterprise |  | Regulated | Live system state |  |  |  |  | Full assurance | Specialize | Risk and compliance avoided |  | Not applicable | 4 Pro-code | Partner |  | Multi-agent: planned growth
Approved | Agent | Another agent | Frontline device |  | 5 External |  |  | Take an action | [5 empty] | Control | Capacity redirected to the mission |  |  | 5 Infrastructure
Building |  |  | External channel | [10 empty] | Adapt | Experience and retention
Piloting | [13 empty] | Act locally
Released | [13 empty] | Build
Parked
Rejected
Stage 4 - assurance tier matrix (consequence x reach). Header row 31, data rows 32-34.
Q8a consequence | 1-2 | 3 | 4-5
Read only | Light touch | Owner approves | Controlled pilot
Writes to a system | Owner approves | Controlled pilot | Full assurance
Real-world effect | Controlled pilot | Full assurance | Full assurance
Tier ordinals. Data rows 37-40.
Tier | Ordinal | What it means
Light touch | 1 | Ship it. Standard guardrails only.
Owner approves | 2 | Named owner signs off. Spot-checked, not gated.
Controlled pilot | 3 | Measured pilot, defined success criteria, a decision gate.
Full assurance | 4 | Evaluations, human in the loop, monitoring, a route to a person.
Stage 5 level 2 - the eight verbs. Data rows 43-50.
Verb | Lands on | Selected by
Assist | Microsoft 365 Copilot | Q1 person already working - Q2 inside the tool they have open - Q8a read only
Delegate | Copilot Cowork | Q1 person asks - Q6 take an action across several M365 surfaces - returns a finished artefact
Monitor | Fabric operations agent | Q1 system event or schedule - Q6 live system state - Q2 no interface, output arrives in Teams
Specialize | Declarative agent / Agent Builder | Q1 person asks - Q6 static documents - Q3 team or function - stable scope
Control | Copilot Studio, standard harness | Q8a writes to a system - consistency and branching matter - analytics and channel publishing
Adapt | Copilot Studio, GitHub Copilot harness | Reasoning-heavy - multi-tool - document-intensive - the path is not fixed
Act locally | Microsoft Scout | Q2 local files, shell or browser - Q5 data that should not leave the device
Build | Microsoft Foundry (+ Foundry Local) | Q3 tier 4-5 - Q5 regulated - Q8a real-world effect - needs evaluation, tracing, VNet
Q5 - what each data class forces. Data rows 53-56.
Answer | What it forces
Public | Must not touch internal sources. Separate environment from internal agents.
Internal | Standard M365 or Foundry standard setup, public networking. Labels honoured.
Confidential | Foundry standard with private networking, or Copilot Studio with data location set. Explicit DLP policy. Named retention period.
Regulated | All of the above, plus consent and residency answered before build, plus retention and deletion mechanisms, plus a named accountable human.
Stage 4 - release gate, the three tests behind each check.
Check | Test 1 | Test 2 | Test 3
1. Accountable | Named business owner | Named technical owner | Intended users and purpose recorded
2. Identifiable | Agent entered in the organisational registry | One distinct identity | Ownership and lifecycle status visible
3. Constrained | Only required data and tools allowed | User-delegated or service identity explicitly chosen | External connections approved
4. Tested | Success and failure criteria defined | Security and adversarial testing completed | Human intervention defined where required
5. Observable | Activity, quality, access and cost monitored | Logs retained according to policy | Alerts routed to the appropriate operational team
6. Recoverable | Kill switch or disable path | Incident owner and escalation path | Rollback, evidence preservation and review process
Stage 2 - benefit types.
Benefit type | Typically | Example
Time or cost released | Hard | Hours returned to a team
Error and rework reduction | Hard | Fewer corrections, fewer escalations
Speed and responsiveness | Hard or soft | Days to hours in a process
Risk and compliance avoided | Soft, sometimes very large | Audit readiness, a missed obligation avoided
Capacity redirected to the mission | Soft | More time with clients rather than fewer staff
Experience and retention | Soft | Reduced administrative burden on frontline staff
Is your human in the loop real?
Real | Theatre
A specific condition triggers review, not 'sometimes' | Everything gets flagged, so reviewers stopped reading
The reviewer sees the reasoning | The reviewer only sees the final output
Rejecting has actually been exercised | Nobody has ever clicked reject
The decision and its reason are logged | No record of who approved what
Stage 1 - four outcomes, and only one is an agent.
Outcome | Test | Goes to | AI governance?
Automation | Steps are clear, repeatable, follow strict rules | Power Automate, Logic Apps, code | No
Predictive or optimisation | Forecasting, scoring, matching or pattern-finding rather than language | Fabric data science, Azure ML, prebuilt Foundry models | Model governance, not agent governance
Retrieval | Static question and answer, or summarising a fixed set of documents | SharePoint agent, Copilot Studio retrieval agent, classic RAG | Light
LLM-augmented workflow | A fixed flow with exactly one intelligent step: summarise, classify, extract, draft | A flow with an AI action, or a scheduled prompt | Proportional to consequence
Agent | Decides its own next step, picks its own tools, copes with messy input | Continue to Stage 2 | Yes, full

## Start here
AI use case decision workbook
The tracking companion to "Turning an idea list into working agents - v5". Eight stages that turn a list of ideas into a prioritised set of projects, where the technology falls out of the answers rather than being the starting assumption. Grounded in the Microsoft Cloud Adoption Framework for AI agents.
How to use it
One row per job | Row 3 on every sheet is the same use case as row 3 on every other sheet. Split vague labels into jobs before you start: one label often covers three or four jobs, each with a different risk profile and a different owner. Phase a use case with a shared ID and the Phase column - UC-06a interim, UC-06b target - and score each phase separately.
Cream cells are yours | Cream cells are inputs. Blue-grey italic cells are calculated - do not type in them.
Work left to right | Register, then Outcome contract, then Eight questions. Assurance and gate, Technology direction and Answers out then fill themselves in.
Blanks are the deliverable | The value baseline and owner cells are usually the emptiest in the workbook and only the customer can fill them. A named, specific list of what is missing is a more useful deliverable than a set of confident guesses. The last column of Answers out builds that list per row automatically.
The eight stages
Stage 0 - Business plan for AI agents | Frame the list. Desirability, feasibility, viability, responsibility. Split vague labels into jobs, deduplicate, allow phasing.
Stage 1 - Is this AI at all? | Four outcomes and only one is an agent: automation, predictive, LLM-augmented, agent, with retrieval alongside as the light case. The highest-value gate in the framework for saving money.
Stage 2 - The outcome contract | The result, the owner, the boundary, the gates, the value baseline. Five things, all before anyone opens a product page.
Stage 3 - The eight questions | None of them names a product. Answer them and the platform, retrieval pattern, identity model, network topology and assurance bar are already determined.
Stage 4 - Assurance tier and release gate | Consequence by reach sets the tier. Q8b lifts it. Regulated data floors it. Then six checks: accountable, identifiable, constrained, tested, observable, recoverable.
Stage 5 - Technology direction | Prefer the lowest rung that works, and read assurance before category. Low-code supports autonomous agents - do not climb a rung you do not need.
Stage 6 - Prove it | Prototype time-boxed, pilot the hardest step, evaluate against the Stage 2 measure, red team, release only once the control has run for real.
Stage 7 - Operate | Monitor the outcome measure not uptime, re-evaluate on a schedule, keep the control staffed, name the back-to-design triggers, audit the estate.
The sheets
Register | Identity, Stage 0 scores, Stage 1 category, and the rollup of every calculated answer.
Outcome contract | Stage 2. The five contract items and the six value baseline measurements.
Eight questions | Stage 3. Q1 to Q8b, plus intended versus pilot reach and the connectivity assumption.
Assurance and gate | Stage 4. Calculated tier with the working shown, then the six-point release gate.
Technology direction | Stage 5. Calculated ladder rung, suggested verb, landing product, run-location constraints.
Prove and operate | Stages 6 and 7. Prototype, evaluation, red team, release, then the run obligations.
Answers out | The eight columns the customer asked for, produced from the stages above.
Scoring | The Cloud Adoption Framework's nine sub-criteria, three axes, 1 to 5.
Lists | Dropdown lists and lookup tables. Formulas point at these ranges - do not reorder.
Decision logic | How every calculated column is derived, in words.
Platform reference | The seven surfaces, what they run on, what they are best for.
References | Cloud Adoption Framework sources, per stage.
Version and status
What this is | An independent decision framework and the author's own professional recommendations. It builds on publicly available Microsoft Cloud Adoption Framework guidance, which is linked at each stage. It is NOT official Microsoft guidance, NOT a Microsoft product, and NOT supported by Microsoft.
Not professional advice | Nothing here is legal, regulatory, clinical, privacy or financial advice. The assurance tiers and governance positions are the author's recommendations, not a compliance standard. Validate against your own obligations and take professional advice where those obligations apply.
No commercial terms | This workbook deliberately carries no licensing, pricing or entitlement information. Those are customer-specific, move quarterly, and are not this framework's to state. Confirm licensing, preview status and regional availability with Microsoft before any recommendation.
Product claims | The framework names capabilities. Where the workbook names a product, treat it as current-as-checked and confirm before rollout.
No warranty | Provided as is, without warranty of any kind. You are responsible for decisions made using it.
Generated | 2026-09-10

## Register
IDENTITY | [8 empty] | STAGE 0 BUSINESS PLAN (1-5 each) |  |  |  |  | STAGE 1 IS THIS AI AT ALL? | [7 empty] | ROLLUP (calculated)
ID | Phase | Use case (one job, one owner, one risk profile) | What it actually does, in one sentence | Business area | Requested by | Status | Date reviewed | Duplicate of / related to | Desirability | Feasibility | Viability | Responsibility (1-5) | Stage 0 total (of 20) | Language or judgement needed? | Forecasting, scoring or matching? | Multi-step decisions? | Many tools or systems? | Adaptive to messy input? | Suggested category | Category (confirmed) | Route if it is not an agent | Assurance tier | Ladder rung | Lands on | Time estimate | Quick win? | Contract complete
UC-01
UC-02
UC-03
UC-04
UC-05
UC-06
UC-07
UC-08
UC-09
UC-10
UC-11
UC-12
UC-13
UC-14
UC-15
UC-16
UC-17
UC-18
UC-19
UC-20
UC-21
UC-22
UC-23
UC-24
UC-25
UC-26
UC-27
UC-28
UC-29
UC-30
UC-31
UC-32
UC-33
UC-34
UC-35
UC-36
UC-37
UC-38
UC-39
UC-40
UC-41
UC-42
UC-43
UC-44
UC-45
UC-46
UC-47
UC-48
UC-49
UC-50
Note on I2: Stage 0: deduplicate and complete the list before classifying anything.
Note on J2: The user desirability axis from the Scoring sheet, rescaled from its 3-15 range to 1-5 so all four Stage 0 lenses are comparable.
Note on K2: The technical feasibility axis from the Scoring sheet, rescaled from its 3-15 range to 1-5.
Note on L2: The business impact axis from the Scoring sheet, rescaled from its 3-15 range to 1-5.
Note on M2: Can we do this responsibly: safeguards, consent, disclosure, fairness. Scored here because CAF's nine sub-criteria do not cover it.
Note on Q2: CAF positive test 1: reads, evaluates, decides, checks its own work.
Note on R2: CAF positive test 2: chooses which API, when, and how to combine results.
Note on S2: CAF positive test 3: interprets intent from incomplete or unclear input.
Note on U2: Leave blank to accept the suggestion. Anything typed here overrides it, and Stage 5 and Answers out follow the override.

## Outcome contract
USE CASE |  | THE CONTRACT - five things, all before anyone opens a product page | [9 empty] | 5 THE VALUE BASELINE - six measurements of the process as it runs today | [8 empty] | CALCULATED
ID | Use case | 1 The result: an outcome with a number, not a feature | Metric that moves | Baseline today | Target | 2 Owner: build | 2 Owner: after go-live | 3 The boundary: what it will explicitly refuse to do | 4 Gate: prototype | 4 Gate: pilot | 4 Gate: release | V1 People doing this work today | V2 Times per person per year | V3 Minutes each time | V4a How often it goes wrong | V4b Cost each time it goes wrong | V5 Metric today | V6 What happens to the time saved | Benefit type | Hard or soft | Annual hours in the process today | Annual cost of getting it wrong | Value baseline captured | Note
Note on C2: "Fewer escalations reach HR" is an outcome. "A chatbot" is not.
Note on E2: Record today's baseline where the process already exists; estimate and refine where it does not.
Note on G2: One accountable name, not a steering committee.
Note on H2: Someone who can say it is working, or pull it back.
Note on I2: This becomes the agent charter: system responsibilities, agent roles, prohibited actions. Without it, agents evolve beyond their intended scope.
Note on J2: Business metrics as decision gates. Go or no-go on the data, not optimism.
Note on M2: The population term in any benefit calculation.
Note on N2: The frequency term, and the best predictor of whether this is worth doing at all.
Note on O2: Converts volume into hours.
Note on P2: The most commonly omitted benefit, and often the largest.
Note on Q2: Rework, escalation, delay, a complaint. Use the customer's own unit.
Note on R2: Mirrors the baseline recorded in the contract. Without a starting number you cannot prove improvement.
Note on S2: The question finance will ask. Hours nobody can point to as redeployed capacity are a slide, not a benefit.
Note on U2: A case built only on soft benefits will be challenged. A case that ignores them will undersell the work. Name both.
Note on Y2: The framework assembles the numbers. It does not price them. Rates, licences and discounts are customer-specific and move quarterly - do the arithmetic elsewhere, dated, and only when a decision turns on it.

## Eight questions
USE CASE |  | Q1-Q4 SHAPE, REACH AND IDENTITY | [6 empty] | Q5-Q8 DATA, CONNECTION AND CONSEQUENCE | [6 empty] | RECORDED, BUT NOT QUESTIONS
ID | Use case | Q1 What starts it? | Q2 Where does the answer land? | Q2b Connectivity assumption | Q3 Intended reach | Q3 Pilot reach | Q4 Whose permissions? | Q4 Identity of record | Q5 What class of data? | Q5 What that forces | Q6 What must it know or do? | Q7 Does the connection exist? | Q7 Source systems | Q8a If it gives a wrong answer | Q8b If it silently does nothing | Ready-made agent available? | Do these users have the licences? | Needs memory between uses? | Will it grow beyond 3-5 functions? | How often the source changes | Retrieval decision record
Note on C2: Four of the five are not a chat experience. Get Q1 wrong and everything downstream is wrong, expensively.
Note on D2: Argue for the top of the list. If the output arrives as a pre-filled field or a notification, there is nothing to adopt and no adoption curve.
Note on E2: Only meaningful for a frontline device. A tool that needs signal fails in a client's home - and that is the setting it was built for.
Note on F2: Design for the destination. Tier 1 needs nothing from governance. Tier 3 is the first real boundary. Tier 5 brings risk and legal into the room.
Note on G2: Deploy at the pilot. Record intended and pilot reach separately.
Note on H2: An agent inherits the permissions that already exist. It does not repair them. Point one at a loose content estate and you have built a very efficient discovery engine for a problem you already had.
Note on I2: Every agent gets one identity, whatever its tier. For a Fabric operations agent this is the creator, not the approver - re-check it when that person changes role.
Note on J2: The only question that decides private networking, data location and retention.
Note on L2: Freshness is the discriminator, and it predicts your timeline. Static documents means weeks. Live system state means months.
Note on M2: If no, the row is integration-led. Have the integration conversation before the AI conversation.
Note on O2: Sets whether evaluations are mandatory, whether a human stays in the loop, and the minimum platform tier.
Note on P2: A missing alert is not a read-only risk. Where a silent failure affects a person, the tier lifts by one.
Note on S2: Ephemeral session memory for transactional agents; persistent memory only for advisory ones.
Note on T2: The third of CAF's three multi-agent criteria. The other two come from Q3 and Q5.
Note on V2: Per data domain: how the agent gets its information and why. Policy documents: search over a governed index. Client status: MCP call. This is what makes an audit answerable later.

## Assurance and gate
USE CASE |  | THE TIER, WITH THE WORKING SHOWN | [12 empty] | RELEASE GATE - no agent moves forward without passing | [7 empty] | CONTROL PLANE BASELINE - applies at every tier, including tier 1
ID | Use case | Q8a consequence | Q3 intended reach | Reach band | Base tier from the matrix | Q8b lift | Q5 floor | Base ordinal | Final ordinal | ASSURANCE TIER | What that means | Named approver | Human in the loop: the trigger condition | Has reject ever been exercised? | 1 Accountable | 2 Identifiable | 3 Constrained | 4 Tested | 5 Observable | 6 Recoverable | Evidence / link | GATE STATUS | Registry entry | Cost tag | Observability | AI involvement disclosed | What happens when the owner leaves
Note on G2: Where a silent failure affects a person, lift the tier by one regardless of the read or write classification.
Note on H2: Regulated data never sits below Controlled pilot, whatever the reach.
Note on N2: A specific condition triggers review, not 'sometimes'. The reviewer must see the reasoning, not just the final output.
Note on O2: If your control has never once said no, it may not be a control.
Note on P2: Named business owner - named technical owner - intended users and purpose recorded
Note on Q2: In the organisational registry - one distinct identity - ownership and lifecycle status visible
Note on R2: Only required data and tools allowed - user-delegated or service identity explicitly chosen - external connections approved
Note on S2: Success and failure criteria defined - security and adversarial testing completed - human intervention defined where required
Note on T2: Activity, quality, access and cost monitored - logs retained according to policy - alerts routed to the appropriate operational team
Note on U2: Kill switch or disable path - incident owner and escalation path - rollback, evidence preservation and review process
Note on V2: Turn governance policy into evidence that can be checked.
Note on X2: You cannot govern agents you do not know exist.
Note on Y2: So token and compute spend can be allocated by department.
Note on Z2: So drift and emerging risk are visible.

## Technology direction
USE CASE |  | LEVEL 1 THE LADDER - read assurance before category |  |  | LEVEL 2 SELECT BY THE VERB | [5 empty] | LEVEL 3 WHERE IT RUNS - hard constraints, or you discover them during a pilot |  |  |  | SHAPE OF THE BUILD
ID | Use case | Suggested rung | Rung (confirmed) | Why | Suggested verb | Verb (confirmed) | Lands on | Selected by | Product (final) | Date checked | Must work with no connectivity | Must run while nobody is present | Data must not leave the device or region | Must extend well beyond launch | Single or multi-agent | Model selection | Memory | Owning team
Note on D2: Leave blank to accept the suggestion. Anything typed here overrides it, and every downstream column follows the override.
Note on G2: Leave blank to accept the suggestion. Monitor is the only machine-initiated verb, and the one most often missing from tool comparison charts. Act locally is never suggested automatically - select it when the work is local files, shell or browser.
Note on J2: Never recommend a preview product to a regulated customer as the plan. Name it as an option to watch, with the general availability position stated.
Note on K2: Date every product claim, and confirm before rollout.
Note on P2: Start multi-agent only if you cross a compliance boundary, multiple teams own separate domains, or growth beyond three to five functions is already planned. Otherwise test a single agent first: latency accumulates at every handoff and cost multiplies.
Note on Q2: Match model capability to task complexity. Smaller models for summarisation and routine work; reserve premium models for complex reasoning, which also carry stricter rate limits.
Note on S2: Platform team owns the foundation and guardrails. Workload teams own the end-to-end lifecycle of specific agents. The AI Centre of Excellence advises and trains.

## Prove and operate
USE CASE |  | STAGE 6 BEFORE RELEASE | [10 empty] | STAGE 7 AFTER RELEASE
ID | Use case | 1 Prototype start | 1 Prototype end | Days | Time-box respected? | 2 The hardest step (not the easiest) | 2 Hardest step piloted? | 3 Evaluated against the Stage 2 measure? | 4 Red team date | 5 Has the control run for real? | Release date | Ready to release? | 1 Outcome measure being monitored | 1 Current value | 1 As at | 2 Re-evaluation cadence | 2 Last re-evaluation | 3 Control staffed by | 4 Back-to-design triggers | 5 Last estate audit | 5 Still in use? | 5 Keep or retire | Consumption review note
Note on D2: Time-boxed to one or two weeks per candidate approach.
Note on G2: Teams instinctively prototype the easiest step because it demos well, which proves nothing.
Note on I2: Against the outcome measure, not a generic quality score. Store evaluations in a shared catalogue so every team applies the same standard.
Note on J2: Prompt injection, data leakage, jailbreak. Mandatory before production and after significant updates, not optional.
Note on K2: Release only once the Stage 4 control has run for real, not just in a test script.
Note on N2: Monitor the outcome measure, not uptime. Uptime tells you the lights are on, not that the number moved.
Note on Q2: On a schedule and after any material change. A system that passed in March has told you nothing about April.
Note on S2: Keep the human control staffed, not just designed. A control with nobody watching it is a diagram.
Note on T2: A near miss, a change in reach tier, a new data source, a policy change. Decide these before they are needed, not while arguing about an incident.
Note on U2: Quarterly. Dormant agents consume quota and expand the attack surface.
Note on X2: Monthly. Find agents using premium models for simple tasks.

## Answers out
USE CASE |  | 1 QUICK WIN AND FEASIBILITY |  |  |  | 2-3 TOOLS AND SKILLS |  | 4-6 COST AND TIME |  |  | 7-8 SUPPORT, AND WHAT WE NEED BACK
ID | Use case | Quick win? | Why not (the first failing test) | Assurance tier | Integration-led? | Tools required | Skills and roles required | Development effort | Operations effort | Time estimate | Microsoft support | Additional information required from the customer | Contract complete
Note on C2: A quick win is: not an agent, reach tier 1-2, read only, internal-or-below data, a static source, and a connection that already exists.
Note on K2: Q6 freshness plus Q7 connection plus the Stage 4 tier. Static and an existing connection means weeks. Live state or no connection means months.
Note on M2: The blanks are not gaps in our analysis. They are the customer's half of the contract, and naming them precisely is more useful than filling them with assumptions. The rows that come back filled in are the rows with a real owner.

## Scoring
USE CASE |  | BUSINESS IMPACT (1-5 each) |  |  | TECHNICAL FEASIBILITY (1-5 each) |  |  | USER DESIRABILITY (1-5 each) |  |  | AXES
ID | Use case | Executive strategy alignment | Business value (the four value areas) | Change management timeframe | Implementation and operation risks | Sufficient safeguards | Technology fit with existing systems | Key personas understood | Value proposition to the user | Change resistance | Business impact (of 15) | Technical feasibility (of 15) | User desirability (of 15) | Total (of 45) | Rank | Note
Note on C2: If a use case does not support strategy, pause it early.
Note on D2: Reshape business processes - enrich employee experiences - reinvent customer engagement - accelerate innovation.
Note on F2: If you cannot name the risks you cannot manage them.
Note on G2: Never advance a use case with unclear safeguards.
Note on H2: Poor alignment increases complexity and risk.
Note on J2: Choose early use cases with motivated users.
Note on Q2: None of CAF's nine sub-criteria is cost. Two ideas can both score 12 out of 15 and be wildly different propositions. CAF scores desirability. It does not score affordability - the Stage 2 value baseline is what lets you separate them.

## Decision logic
How every calculated column is derived
Calculated column | Lives on | How it is derived
Suggested category | Register | Forecasting, scoring or matching = Yes gives Predictive. Otherwise language or judgement = No gives Automation. Otherwise all three CAF positive tests true (multi-step, many tools, adaptive) gives Agent. Otherwise multi-step and many tools both No gives Retrieval. Everything else is an LLM-augmented workflow.
Confirmed beats suggested | Register, Technology direction | Three columns come in suggested and confirmed pairs: the Stage 1 category, the ladder rung and the verb. Leave the confirmed cell blank and the suggestion flows straight through to every downstream column, so nothing stalls. Type anything into the confirmed cell and the override wins everywhere. This is where human judgement enters the model: the suggestion is a default, not a decision.
Stage 0 lenses | Register | Desirability, feasibility and viability are pulled from the three CAF axes on the Scoring sheet and rescaled from their 3-15 range to 1-5, so all four lenses carry equal weight. Responsibility is scored directly on the Register, because none of CAF's nine sub-criteria covers it. The total is out of 20.
Annual hours in the process today | Outcome contract | V1 people x V2 times per person per year x V3 minutes, divided by 60. Blank unless all three are present. This is a fact about the current process, not a benefit claim.
Annual cost of getting it wrong | Outcome contract | V1 x V2 x V4a error rate x V4b cost each time. The most commonly omitted benefit, and frequently the largest.
Q5 what that forces | Eight questions | A straight lookup of the data class against the Q5 table on Lists. Q5 is the only question that decides private networking, data location and retention.
Base tier from the matrix | Assurance and gate | Q8a consequence against the reach band from Q3 intended reach. Read only gives light touch, owner approves, controlled pilot. Writes to a system gives owner approves, controlled pilot, full assurance. Real-world effect gives controlled pilot, full assurance, full assurance.
Assurance tier | Assurance and gate | The base ordinal, plus one if Q8b says a silent failure affects a person, then floored at three (controlled pilot) if Q5 is regulated, then capped at four. A read-only clinical assistant used by one person is not a light touch item.
Gate status | Assurance and gate | Passed only when all six release-gate checks are answered and none is Not met or In progress. Any Not met gives Blocked. Fewer than six answers gives Incomplete.
Suggested rung | Technology direction | Automation or predictive gives rung 1. Then assurance is read before category: regulated data, a real-world effect or a full assurance tier escalates to rung 4 regardless of how simple the category looked. A ready-made agent plus a static or no-knowledge source at tier 1-2 gives rung 2. Everything else is rung 3, low-code, which does support autonomous agents.
Suggested verb | Technology direction | A system event, a schedule or another agent gives Monitor, the only machine-initiated verb. Enterprise or external reach, regulated data or a real-world effect gives Build. A person already working, inside the tool they have open, read only gives Assist. Take an action gives Delegate. Writes to a system gives Control. Static documents gives Specialize. Everything else is Adapt. Act locally is never suggested automatically: select it manually when the work is local files, shell or browser.
Lands on | Technology direction | A lookup of the confirmed verb against the eight-verb table on Lists. Product names are volatile, so record the final product and the date it was checked in the two columns beside it.
Level 3 constraints | Technology direction | Connectivity from Q2b, unattended running from Q1, data locality from Q5, extensibility from intended reach exceeding pilot reach. These are hard constraints you will otherwise discover during a pilot.
Ready to release? | Prove and operate | Yes only when the hardest step was piloted, an evaluation exists against the Stage 2 measure, the control has run for real, and the Stage 4 release gate has passed.
Quick win? | Answers out | Not an agent, reach tier 1-2, read only, public or internal data, nothing or static documents as the source, and a connection that already exists in production. Any single failure disqualifies it, and the next column names the first failing test.
Time estimate | Answers out | No connection gives months and the row is integration-led. Live system state or take an action gives months. Analytical data gives weeks to months. Otherwise weeks, extended by a full assurance cycle where the tier demands it.
Additional information required | Answers out | Concatenates the name of every blank Stage 2 contract cell, every blank value baseline measurement, and any blank Q1, Q5, Q7 or Q8a answer. This column is the deliverable back to the customer.
Three rules that are easy to get backwards
Calculated column | Lives on | How it is derived
Read assurance before category | Stage 5 | Branching on category first is how a clinical scribe gets correctly rated full assurance and is then still described as 'a flow with an AI action'. If the tier is controlled pilot or full assurance, the direction escalates regardless of category, and the row must not be described as a simple flow.
Q8b is a separate failure | Stage 4 | Rating only what the system does when it is wrong misses what happens when it quietly does nothing. A notification agent scores read only. The real risk is the missing alert, not the wrong one.
Low-code reaches autonomous | Stage 5 | CAF's published comparison shows Copilot Studio supporting autonomous agents, not just retrieval and task. Only the ready-made tier is capped. Teams routinely jump to pro-code for adaptive behaviour they could have had a rung lower, and pay for it in build cost and time.

## Platform reference
Capability comparison only. Licensing, cost and commercial terms are deliberately excluded - they are customer-specific, move quarterly, and are not this framework's to state. Confirm licensing, preview status and regional availability with Microsoft before any recommendation.
Surface | What it is for | Runs | Availability | Extensibility | Out of the box | Best for
Microsoft 365 Copilot | Assist me in the flow of work | Cloud | Online | Moderate. Extend through agents and connectors | Work IQ, chat, and assistance in Word, Excel, PowerPoint, Outlook and Teams | Quick Q&A, drafting, summarising, analysis, and in-app personal productivity
Copilot Cowork | Delegate outcomes across Microsoft 365 | Cloud | Online; works while your device is closed | High. Custom skills and plugins | Plans and executes steps across email, calendar, Teams, files, Office artefacts, research and automations | Long, multi-step cross-app work that should return a finished artefact or a completed action
Declarative agent / Agent Builder | Create a focused, reusable helper | Cloud | Online inside Microsoft 365 Copilot | Low to moderate. Knowledge first; advanced actions need Studio or dev tools | Fast no-code setup with instructions plus SharePoint, web and connector knowledge; easy internal sharing | Onboarding, policy Q&A, coaching, and narrow domain assistants with a stable scope
Copilot Studio - standard harness | Control the conversation and workflow | Cloud | Online; multi-channel | High. Topics, flows, connectors, APIs and MCP | Knowledge, prompts, topics, branching, actions, analytics, governance and channel publishing | Help desk, FAQ, guided support, and structured workflows where consistency matters
Copilot Studio - agentic harness | Automate adaptive business processes | Cloud sandbox | Online; internal or external | Very high. Tools, skills, memory, agents and MCP | Goal decomposition, recovery, native Office and PDF work, model choice, connected agents and monitoring | Reasoning-heavy, document-intensive, multi-tool processes with exceptions and changing paths
Microsoft Scout | Let an agent work on my desktop | Hybrid desktop and cloud | Online required | Very high. Local skills, shell, browser and subagents | Local files, shell, browser automation, Microsoft 365 actions, Office artefacts, memory and automations | Power-user or developer work needing local files, builds and tests, browser tasks, or background automation
Microsoft Foundry + Foundry Local | Build a custom agent product or platform | Cloud or on-device | Online, or offline with Foundry Local | Maximum. Code, models, MCP, APIs and containers | Prompt and hosted agents, model catalogue, toolboxes, identity, VNet, evaluation, tracing and observability | Custom apps, production-scale agents, multi-agent systems, special protocols, or private offline use
Cowork and Scout do the same job in different places. Cowork is delegation to your tenant. Scout is delegation to your machine. If the work touches local files, a shell or a browser, it is Scout. If it touches your mail, calendar, Teams and documents, it is Cowork.
CAF's published comparison: ready-made SaaS agents support retrieval and task only. Copilot Studio supports retrieval, task and autonomous. Foundry and GPUs or containers support all three. Only the ready-made tier is capped - do not climb a rung to reach adaptive behaviour you could have had a rung lower.
Fabric has two agents and they are not interchangeable. The data agent answers questions a person asks, over lakehouse, warehouse, semantic model or KQL data, and takes no action. The operations agent evaluates continuously, watches an eventhouse or ontology for a condition, then messages a person in Teams with a recommended action that only runs when they approve it. The distinction is exactly Q1.
Some surfaces listed here may be in preview or have limited regional availability. This table describes capability shape, not availability or entitlement. Treat every product name as current-as-checked and verify before relying on it.

## References
Cloud Adoption Framework sources
Stage | Page | Link
Overall | AI agents in the Cloud Adoption Framework | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/
Stages 0, 1 and scoring | Business plan for AI agents, and when not to use AI agents | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/business-strategy-plan
Stage 2 and Stage 6 | Build and secure the process, define the agent charter, agent observability | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/build-secure-process
Stage 3 - technology | Technology plan | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/technology-solutions-plan-strategy
Stage 3 - data | Data architecture plan, retrieval strategies and data placement | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/data-architecture-plan
Stage 4 | Govern and secure AI agents across the organisation | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/governance-security-across-organization
Stage 4 | Responsible AI policies | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai/responsible-ai-policies
Stage 5 | Single agent or multiple agents | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/single-agent-multiple-agents
Stage 5 - Fabric | Create and configure operations agents | https://learn.microsoft.com/fabric/real-time-intelligence/operations-agent
Stage 5 - Fabric | Fabric data agent | https://learn.microsoft.com/fabric/data-science/concept-data-agent
Stage 7 | Integrate, manage and operate AI agents | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/integrate-manage-operate
Across every stage | Organisational readiness | https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/ai-agents/organization-people-readiness-plan
What is Microsoft's and what is ours. The eight questions, the five reach rungs, the assurance matrix, the eight verbs and the Q8b omission test are our packaging. That governance obligation changes with scope, that every agent needs a distinct identity, that adversarial testing is mandatory, that agents should sit in the tools people already use, and that low-code supports autonomous agents, are all Microsoft's published guidance.